Item 5 – Checklist Committee Support Document

California Building Standards Triennial Code Adoption Cycle

## 2021 TRIENNIAL CODE ADOPTION CYCLE DATES

- Sept 2020 – March 2021: State Agency Workshop phase; public participation.

- Feb 1, 2021: Initial submittals of proposed code changes for IAPMO, Green and NEC are due

- May 3, 2021: Initial submittals of ICC proposed code changes are due

- May 2021 – Aug 2021: The Code Advisory Committee meeting phase; public participation. The committees are:

  - ACCESS, Accessibility; BFO, Building, Fire and Other; GREEN, Green Building; HF, Health Facilities; PEME, Plumbing, Electrical, Mechanical and Energy and SDLF, Structural Design and Lateral Forces

- July 2021 – Oct 2021: 45-day Public Comment Periods; public participation. Proposed actions are added to the California Regulatory Notice Register

- Nov 1, 2021: Final submittals from the state agencies are due

- Dec 2021 – Jan 2022: Commission meetings are held for adoption and approval of proposals; public participation. Subsequently filed with the Secretary of State

- Feb 2022 – July 2022: Codification and publication period

- July 1, 2022: Publication date for all parts of Title 24

- July 2022 – Jan 2023: Statutorily required 180-day period between the publication date and the effective date.

- Jan 1, 2023: Effective date of the 2022 California Building Standards Code