## RACI
e-Signature Solution Roles and Responsibility Matrix
Last Updated: November 30, 2018
| Department |  | Vendor | Information Technology |  |  |  |  | Forms | External Agencies
| Governance (purchasing, procurement, legal, IT) | End Users | DocuSign | Tool System Admin | Azure Admin | ISO | Business Analyst | Project Manager | Forms Manager (Dept) | CDT | SCO | Forms Mgmt Center
Develop Internal Policy (Administrative Order) | A,R | I |  | I |  | C | I |  | C |  | C
Perform eSignature Business Process Analysis | C | C |  | I |  | C | R | A | C |  | C
Tool Evaluation | I |  |  | R |  | R | R | A | R
ISO Review - eSignature Solution | I |  |  | R |  | A,R | R | R | C |  | I
Service Provider Selection | I |  | I | R |  | R | R | A | C |  | C
Purchase Order Creation |  |  | I |  |  |  | I | A |  | I
Activate Admin Account - Sandbox and Production |  |  | A,R | R |  |  | I | I
Active Single Sign On |  |  | A,R | R | C |  | I | I
Provide Basic Admin Trainings |  |  | A,R | R |  |  | C | I | R
Customize eSign Portal User Experience |  |  |  | A,R |  |  | C | I | C
Maintenance and Operations
Develop eSignature tool workflow/templates |  | C |  | A,R |  |  | R
Develop\Update Departmental form Templates |  | C |  | I |  |  | C |  | A,R
Develop\Update STD form Templates |  | C |  | I |  |  | C |  | R |  |  | A
User Administration |  | I |  | A,R |  |  | C
End User Tranining |  | R |  | C |  |  | A,R |  | C
Develop Custom Usage Reports |  | C | C | A,R |  |  | R
Tool Service Monitoring/Upgrades |  | I | C | A,R
Tool Usage Monitoring | I |  | C | A,R
Responsible: | Staff that is responsible for doing the work for the task
Accountable: | Individual who has authority to approve or disapprove task
Consulted: | People who are consulted and provide input into the tasks
Informed: | People who need to be informed about the task